Nov. 7, 2014

- GUIDELINES

- FOR POTENTIAL HOSTS BIDDING FOR ISDE SYMPOSIA

- APPROVED BY ISDE COUNCIL IN NAGOYA; JAPAN

- NOVEMBER 7th 2014, ISDE NAGOYA BIDDING GUIDELINES

| - Introduction - 1.1 The International Symposium on Digital Earth is an academic platform of the International Society for Digital Earth (ISDE), which gathers together people from scientific, enterprise, education, and management fields to discuss digital earth related theories, technologies and applications in light of the progress of digital earth and its vision perspective. - 1.2 The International Symposium on Digital Earth was launched in 1999 in Beijing. With the promulgation of 1999 Beijing Declaration on Digital Earth and establishment of the International Steering Committee of the International Symposium on Digital Earth in 2000, as well as the establishment of the International Society for Digital Earth, the Symposium has been convened every two years since 1999 and rotated in different continents. - 1.3 Purpose: The ISDE symposia series is the major international event relating to the progress and advances in the science, technology and applications relating to DE. The ideal length of the symposium is three to four days. Planning for the next Symposium should start at least 24 months before the next Symposium. A draft outline of the planning schedule is given below. The Society shall be the primary organizer of all Symposia. Partnering sponsors must be selected and identified well in advance, and approved the local host of the ISDE symposium. |  |
| --- | --- |
| - 2. Conference Facilities and Accommodation - Conference facilities should be selected according to the most suitable options for the host country. They may be in a hotel, rented facilities, or within the host's facilities, e.g. university lecture theatres. The location of housing and the conference in the same venue ('residential format'), in a hotel or in a university college, is a suitable option, since it facilitates contact and discussions between the participants, and generates a good workshop-like atmosphere. Common lunches further add to exchange between the participants. It is preferable for the accommodation to be organized by a local organization, since it reduces the workload associated with this task. - 2.1 Facilities and equipment - An appropriate theatre-type venue for the Opening and Closing Ceremonies which will amply accommodate the total expected attendance, equipped for electronic and viewgraph projection. - ISDE prefers that Symposia offer at least one Plenary, and a number of parallel Technical Sessions in school-room-setup. However, when expected attendance warrants multiple parallel sessions, then rooms for parallel Technical Sessions should have a school-room-setup capacity of a minimum 50-100 persons in each, equipped for electronic projection and normal audio-visual equipment. - A sample poster space to allow for up to 30 simultaneous poster presentations. - A small office with table and seating space for 15-25 individuals for the ISDE Council meeting and IJDE Editorial Board meeting. - A minimum of 10 Internet access sites for Symposium participants to use on a paid or complimentary basis and preferably free wifi - If appropriate, an exhibit hall to accommodate the commercial and scientific exhibit. - Speakers check-in and rehearsal room equipped with equipment for slides, overheads and electronic projection and equipped with a large table with chairs. - Registration and information desk. - Travel agency facilities. - A rendez-vous point. - Signs for all session rooms listing in detail, the sessions and presenting authors, the Poster Session rooms, and the Local Organizing Committee Office. - 2.2 Staff - The Host shall provide: - A designated individual to serve as Symposium Manager, who will have final responsibility for all aspects of the Symposium operation. The Symposium Manager will establish a Symposium Committee which will organize the technical program in coordination with the Working Group Chairs and Co-Chairs, all financial aspects, the secretarial work, the social events, and where appropriate the scientific exhibit and the technical tours, and attend to special tasks such as press relations, travel bureau relations, etc. - Adequate on-site staff to ensure the smooth operations of the registration and information desks on a daily basis throughout the Symposium. - On-site staff to ensure the smooth operations of audio-visual equipment at all Technical, Poster and tutorial sessions. |  |
| - 3. Technical Program The Technical Program, including the review of the abstracts and their acceptance, should be determined by the ISDE and the local organizers, in consultation with the Council and the Secretariat. Notification or rejection of abstracts should be sent to all authors at least 6 months prior to the Symposium. The final program should be distributed on the Web and also by email. Organisers should ensure that all speakers will attend the Symposium by confirming by e-mail and/or advanced registration. During the Symposium the local organizers must inform each Chairman of a technical session about any no-show that has been identified in the last days (or hours). This will enable the Chairman to restructure the technical session accordingly. |  |
| - 4. Structure of Symposium 4.1 The Symposium Opening should include a VIP from the host country, and a keynote speaker invited by ISDE who identifies the important developments in the Society’s activities since the last Symposium. 4.2 Keynote papers and/or sessions on relevant inter-disciplinary topics through other international bodies should be included in the Symposium. These shall be proposed by the Scientific Program Committee, which shall consist of both host country scientists and ISDE Council Members. |  |
| 4.3 The Symposium program may be based on single-sessions, parallel sessions, or a mix of single and parallel sessions, depending on the number of papers to be presented. The latter enables the focus of sessions on specific topics and/or the provision of plenary sessions. 4.4 Oral Sessions should normally last 90 minutes, comprising four or five speakers. A time allocation of about 15-20 minutes for each speaker leaves sufficient time for questions. Furthermore, it ensures that the time slots for each speaker are not overrun, which is a requirement when there are parallel sessions. 4.5 Poster sessions should be included in the program, with brief presentations (approx. 3-5 minutes each) by the authors. Posters should be allocated ½ day each for their presentation, with the authors present at their posters. |  |
| 5. Exhibition A Commercial Exhibition should be included in the Symposium. An "Exhibitor's Showcase Session" provides the exhibitors with an opportunity to present themselves to the participants, and hence integrates them into the symposium. The rates to be charged for commercial exhibitor’s spaces will be determined by the Symposium Organizers, and should be at the “going rate” for the venue. |  |
| - 6. Sponsorship - The host organization will try to find as many financial “Sponsors” as possible to support the symposium. The largest sponsor (platinum) will be given opportunity to make a presentation at a Plenary Session. Sponsors should also be sought for other symposium events, such as Welcome Reception, Gala Dinner, Conference Bag, etc. Sponsors will be duly acknowledged in all materials related to the event (website, brochures, proceedings, announcements, etc.). |  |
| - 7. Announcement and advertising - 7.1 Posting on the Society website and distribution of announcements on the Symposia, as well as those of the Partner organizations should be a primary means of advertising and promoting the Symposia. - 7.2 Advertisements should also be placed in the International Journal of Digital Earth (IJDE), as well as other journals, Newsletters and especially during other conferences. The Secretariat will maintain an address listing for journals and other events. 7.3 The Local Organizing Committee will keep the Council informed of the plans and progress for the Symposium and for providing draft copies of Symposium brochures and related materials to the Council. |  |
| 8. Abstracts Electronic submission of the abstracts via E-mail has the advantage in that they can be posted on the Web and Society websites. All abstracts, and Symposium timetable when available, be placed on the Web. |  |
| - 9. Finance 9.1 The Local organizer must elaborate a complete Budget proposal, including base facility costs, management or coordination charges and overhead, advertising, publication and promotion, printing and distribution, salaries and commissions, set-up and equipment rental charges, take-down and transportation charges, refreshment availability and costs, etc. A 10% budget contingency must be added. Also, a 10% surplus to be provided to ISDE may not always be possible, but shall be budgeted for and shall be paid when the event runs at a surplus. 9.2 On the revenue side, the Budget must include anticipated or potential revenue from all sources, including: registration fees, exhibitor charges, advertising returns, sponsorship fees, governmental contributions, and all other sources of actual or potential revenue. If applicable, in-kind contributions should be described separately. It is always difficult and not accurate to estimate the value of any in-kind contribution. 9.3 Following the Symposium or Summit, the organisers will provide a full set of financial accounts to the ISDE setting out all transactions including those that are pending. The Organiser institution is obliged to conduct an independent audit of the final accounts and have this complete with six months of the date of the Symposium or Summit. Should revenue from all sources have exceeded expenses, resulting in a surplus, the Host Organizer and ISDE will share this on a 50-50 basis. This amount will be sent to the ISDE Secretariat within 30 days of the end of the Symposium or Summit, noting that this amount may be adjusted after the final audit. 9.4 The Host shall have complete financial responsibility for all aspects of the Symposium organization. ISDE will not provide any funds for this purpose. A formal contract shall be signed between the Host and ISDE within thirty days of a successful BID, confirming all scientific, financial and other arrangements. The ISDE will not underwrite the cost of the Symposium or Summit. 9.5 The Host shall provide rooms for ISDE Council meeting and IJDE Editorial Board meeting free of charge. 9.6 The ISDE shall receive a maximum of 6 free registrations, from which at least 3 registrations will go to the ISDE Secretariat. ISDE shall then see the best way to distribute the remaining three waived registrations among the ISDE Secretariat and ISDE members. 9.7 It is suggested that the Host institution could consider offering a reduced registration for young professionals (under 30 years) and seniors (over 65 years). This is only a suggestion, not a mandatory clause. |  |
| - 10. Publication of Proceedings of Symposium |  |
| 10.1 | All Symposia proceedings will be published in hardcopy and/or in an appropriate electronic support (CD, USB-key, etc.). |
| 10.2 | Proceedings may be available to registrants at the Symposium. |
| 10.3 | Selected papers may be published in ISDE’s Journal: IJDE. It may be possible for hosts to act as Guest Editors of a dedicated “Special Issue” of IJDE. |
| - 11. Awards Best poster awards and young authors' awards are encouraged. The decision of the awards can be made in advance of the Symposium based on the submitted paper, or during the symposium based on the paper and its oral presentation. Awards should be presented at a plenary session, or other event. Awards are oriented to young professional making particularly good efforts to elaborate or present a paper and/or poster. For example, senior representatives of large companies who have a large amount of assistance should not be considered for awards. |  |
| - 12. Suggested Schedule for Symposium and Summit Planning Site selection (see Guidelines for Proposals to Host) Finalise and sign agreement with the Council and Secretariat First announcement and initial call for Exhibits Second Announcement and Call for Papers Deadline for abstracts Notification of acceptance Early Registration Final Program; 24 months before the Symposium 21 months prior to Symposium 15-18 months prior to Symposium 9-12 months prior to Symposium 6 months prior to Symposium 4 months prior to Symposium 2 months prior to Symposium about 1 month prior to Symposium. |
| - 13. Public outreach programme The Host should organize jointly with the ISDE, a Public Outreach Program consisting of public lectures, local TV and radio coverage and other planned activities oriented on the public within The Host country. The Host will be responsible for creating and disseminating the publicity for the event. |  |
| - 14. Visas - The Host shall send a letter of invitation (without promise of financial support) upon request to potential participants. The Host shall take all measures with its government officials required to assure that all potential participants will be issued appropriate visas according to the 1958 declaration adopted by the International Council of Science (ICSU) concerning non-discrimination on the basis of politics, nationality, religion, race or gender, and unimpeded entry and exit, subject to local law. |  |
| - 15. Insurance - The Host shall provide adequate third party liability and casualty insurance coverage, subject to local law, for the duration of the Symposium for all participants from lesser developed countries duly registered 30 days before the opening of the Symposium. For this purpose, The Host shall present to the ISDE, prior to the Symposium, proof of insurance in the form of an Insurance Policy in the English language (or a certified translation thereof). |  |
| - 16. Security Measures - The Host shall coordinate with the official and regular channels of The Host country for appropriate security measures for the protection of participants and accompanying persons, working equipment and belongings at the Symposium venue and organized Symposium events. |  |
| - 17. Compensation for Damages - The Host shall hold ISDE free from liability for any and all damages resulting from any claims or judgments in favor of third parties, governmental or other entities, for any acts or omissions occurring during the Symposium and its related events. |  |
| - 18. Publicity - 18.1The official ISDE logo shall be prominently displayed on all public documents. - 18.2 In addition to distribution of announcements, an Internet site for ISDE shall be established and maintained to include all announcement information plus links to the ISDE, IJDE home page and other relevant sites. |  |
| - 19. Social Events - A social program for participants shall be arranged by the Host and be provided free of charge or at a reasonable fee. |  |
| - 20. Information that must be provided in a Proposal to host an ISDE Meeting |  |
| - In addition to confirming acceptance of, and explaining how the Host organization will deal with items 1 to 19 above, the Proposal MUST include the following details: |  |
| - 20.1 The name of the Host Institution or organization, the names of Chair of the Organizing Committee, a list of all Committee Members, and their individual experience in hosting international events. |  |
| 20.2 The proposed date and location(s), other dates available, and including dates that are not available. |  |
| - 20.3 A full outline of the past experience of the Host Institution in organizing international events and conferences, including names and contact information for previous events. |  |
| - 20.4 Complete information on the event location(s), complete description of the facilities available for the meeting, accommodation availability, distances to the venue, transportation and costs to and from airport(s), other means of ground transportation to the venue, etc., Hotel rate ranges and star ratings, as well as other possible accommodation in the vicinity of the venue. |  |
| - 20.5 A complete time-line and schedule for all announcements, advertising and promotion to be developed and distributed, by whatever means, in preparation for the event, including all associated costs. |  |
| - 20.6 A description of tourist attractions and facilities or entertainment that might be of interest to delegates and others attending the meeting, for before and after the event. |  |
| 20.7 A full description of the overall in scope of the meeting (its theme, proposed session titles, number of sessions and presentations), including any other associated conferences that may be held in conjunction with the ISDE meeting, and the expected or estimated number of attendees under all options identified. |  |
| 20.8 A full set of financials. |  |
| - Final note - 1) These guidelines suggest an overall procedure to organize an ISDE event. If any item and/or additional items must be modified or included in order to adapt to the national legislation or local procedure, the Local Organizer shall discuss such issues with the ISDE Secretariat. The main objective is to have a well identified framework, agreed by both Parties, that guides the implementation of the ISDE event. - 2) These guidelines shall become a living document that needs to be adapted and modified according to new issues identified. However, in order to assist the Local Organizer, once an Agreement has been signed between the ISDE Secretariat and the Local Organizer, the guidelines of the date of the Agreement shall apply. Any further modification to the “guidelines” shall only be considered as valid for future ISDE events, not for the near future event that has already agreed considering the current existing guidelines. - 3) To facilitate the identification of the valid “guidelines version” under consideration, each version shall have a clear date and if possible a place name, for example these guidelines could then be called the “November 7th 2014, ISDE- Nagoya bidding guidelines”. |  |